20 May 2022
Evaluations of three FNS
programmes in West Africa:
CORIP, SWAPP, HortiFresh
Authors
Nienke Oomes, Debbie Keijser, Bert van Manen, Rodrigo Bustamante, Nicolas Berthiaume and Hilde van Dijkhorst
Commissioned by
Dutch Ministry of Foreign Affairs / Embassy of the Kingdom of the Netherlands in Accra
Final synthesis report

---
TABLE OF CONTENTS
Introduction
Overview of evaluated FNS programmes
Data sources
Key findings
Broader findings at MFA level
Conclusions and recommendations

---
1. INTRODUCTION
The Embassy of the Kingdom of the Netherlands in Accra (EKN Accra) commissioned SEO Amsterdam Economics and MDF Training & Consultancy to conduct the final evaluations of three Food & Nutrition Security (FNS) programmes:
  1. Cocoa Rehabilitation and Intensification Programme (CORIP)
  1. The Sustainable West Africa Palm Oil Programme (SWAPP)
  1. HortiFresh (HF)
Each sub-evaluation was based on a mixed-methods approach, using a variety of quantitative and qualitative data collection and analysis methods (see Section 3). This included fieldwork (interviews, focus group discussions, surveys) in Ghana, Côte d’Ivoire, Sierra Leone, and Liberia, conducted in autumn 2021.
Following the three FNS evaluations, the evaluation team conducted additional interviews and validation sessions with various stakeholders from the Dutch Ministry of Foreign Affairs (EKN Accra, IGG, IOB, DDE) and the Netherlands Enterprise Agency (RVO), combined with a review of other relevant evaluation reports and policy documents, so as to draw broader lessons learned and make recommendations at a higher level.
This report compares and contrasts the key results of the three evaluations, comparing the relative strengths and areas of improvement for each intervention model, and makes recommendations that we hope can be used by MFA and others to improve future food security and private sector development programmes in West Africa and beyond.

---
2. FNS EVALUATION 1: CORIP
The Cocoa Rehabilitation and Intensification Programme (CORIP) – Phase 2
EKN Accra committed €7 million to the first phase of CORIP
EKN Accra committed €14 million to the second phase of CORIP
Countries: Ghana, Cote d’Ivoire, Liberia & Sierra Leone
Aim: stem the long-term decline of the cocoa sector in West Africa by upgrading and intensifying cocoa production
CORIP Phase 1: 2013-2017
CORIP Phase 2: 2018-2021
The core of CORIP was the setup and funding of Rural Service Centres (RSCs) that provide cocoa farmers inputs, training and labour services. In Côte d'Ivoire, cooperatives often played this role.

---
2. FNS EVALUATION 2: SWAPP
The Sustainable West Africa Palm Oil Programme (SWAPP) – Phase 2
EKN Accra committed €12 million to the first phase of SWAPP
EKN Accra committed €13 million to the second phase of SWAPP
SWAPP activities in Ghana were co-funded by the Swiss Secretariat for Economic Affairs (SECO)
Countries: Ghana, Cote d’Ivoire, Liberia & Sierra Leone
Aim: improve the livelihoods of farmers, millers, and other actors in the palm oil supply chains in West Africa
SWAPP Phase 1: 2012 -2016 (in Ghana and Nigeria) SWAPP Phase 2: 2018-2021
SWAPP provided technical assistance and financing for the set-up and operation of SME oil palm mills, SME service centres, farmer organisations and cooperatives, and other oil palm sector agencies.

---
2. FNS EVALUTION 3: HORTIFRESH
HortiFresh (HF) – successor of GhanaVeg
EKN Accra committed €4 million to the GhanaVeg
EKN Accra committed €9 million to HortiFresh
Countries: Ghana & Cote d’Ivoire
Aim: contribute to a sustainable and internationally competitive fruit and vegetable sectors in Ghana and Cote d’Ivoire
GhanaVeg: 2013-2017 (in Ghana)
Hortifresh: 2018 – June 2022
HF supported the fruit and vegetable sector through three funds: cluster, innovation and youth employment fund. Working mainly through partnerships.

---
3. data sources - for the 3 FNS evaluations

---
4. key findings – FNS or PSD?
The ‘FNS’ element of these FNS programmes was limited, while they did have strong Private Sector Development (PSD) characteristics:
The FNS relevance of all three programmes was mixed:
  - Highly relevant for the core FNS policy goal “Inclusive and sustainable growth in agriculture”
  - Somewhat relevant for the FNS goal “Ecologically sustainable food production systems”
  - Less relevant for the FNS goal “End hunger and malnutrition”, as target indicators for nutrition were already met at baseline, and the focus was on countries with less food insecurity (Ghana, Côte d’Ivoire).
All three ‘FNS’ programmes in fact seemed more relevant for PSD than for FNS:
  - Focus on job creation, income growth, access to finance, SME development, trade promotion.
  - While SWAPP and HF had a domestic market component, CORIP focused on an export crop (cocoa).
  - Nutrition awareness was not prominent in the programmes’ intervention logic and activities.
  - Some FNS results indicators looked misplaced (e.g., reduce hunger)
  - A ‘food systems approach’ was not (yet) developed
Similar conclusions have been drawn elsewhere: in our 2SCALE mid-term evaluation, and at the regional conference on FNS< PSD and agribusiness in West Africa, November 2021

---
4. key findings - Overarching results (1)
All three programmes were designed to contribute to three overarching results as defined by the Embassy:
Small-scale food producers with increased productivity/income (PSD & FNS)
Hectares of farmland used more eco-friendly (FNS)
Jobs created and people employed (PSD)

---
4. key findings - Overarching results (2)
Result 1. Small-scale food producers with increased productivity/income
CORIP and SWAPP farmers were not basic food producers, but engaged in cash cropping, the indirect assumption being that increased income would result in better access to (purchased) food. M&E data and fieldwork findings suggest that CORIP and SWAPP farmers raised incomes, but less than expected. Farmers also received assistance with developing alternative (more diversified) livelihoods, including food cropping.
HortiFresh: incorporated the indicator Number of family farms with increased productivity and/or income, and exceeded its target for this indicator. Outgrowers confirmed to have increased their productivity, and saw this as partially resulting from the training received on GAPs.
  - Although it was difficult to attribute this to HF in the absence of a control group and counterfactual.
CORIP
# farmers with 30% increased income
Target: 136,500
Achieved (end-2021): 49,146
SWAPP
% increase in oil palm farm income of beneficiary producers
Target: 75% - 33,542 farmers
Achieved (end-2021): 20,979
HortiFresh
# of family farms with increased productivity and/or income:
Target: 1,500
Achieved (end-2021): 9,347

---
4. key findings - Overarching results (3)
Result 2. Hectares of farmland used more eco-friendly
  - CORIP and SWAPP adopted this as an impact indicator, validated through outcome surveys that checked adherence to selected indicators of good agricultural practices. Both programmes were achieving their targets.
  - HortiFresh did not adopt any indicator that measured their contribution to more eco-friendly use of land.
  - None of the 3 FNS programmes had a counterfactual for this area (no control group, no benchmark)
CORIP
# hectares of farmland brought under sustainable and climate resilient production
Target: 193,000
Achieved (end-2021): 181,426
SWAPP
# hectares of farmland brought under sustainable production
Target: 73,000
Achieved (end-2021): 71,154
HortiFresh
No indicator

---
4. key findings - Overarching results (4)
Result 3. Jobs created and people employed
  - Both CORIP and SWAPP had job creation targets. Both fell short of their targets.
  - HortiFresh targeted and tracked its progress on the indicator ‘Number of reliable jobs created by HortiFresh supported SMEs/Businesses’, and achieved its target.
  - None of the 3 FNS programmes had a counterfactual for employment (no control group, no benchmark)
  - Our contribution analysis suggests that:
    - CORIP did contribute to employment in RSCs, including women and youth.
    - SWAPP contributed to increased jobs in oil mills.
    - HortiFresh grant partners in Ghana employed additional workers and increased the number of farmers to increase product supply.
CORIP
# jobs created and retained
Target: 9,900
Achieved (end-2021): 4,468
SWAPP
# jobs created and retained
Target: 15,050
Achieved (as of end-2021): 1,098
HortiFresh
# of reliable jobs created by HortiFresh supported SMEs/Businesses:
Target: 1,500
Achieved (end-2021): 3,066

---
4. key findings - RELEVANCE (1)

---
4. Key findings - RELEVANCE (2)
Needs assessment and relevance (1)
Not all programme interventions were sufficiently relevant. The project formulation did not invest sufficient time and expertise, some assumptions turned out to be incorrect, and project appraisals and feasibility assessments were not sufficiently rigorous.
Examples of design weaknesses that could have been avoided:
  - The access to finance (A2F) strategy for CORIP and SWAPP was not in line with international practice. Impact investors typically finance trade operations and larger businesses, but do not finance SMEs such as artisanal oil mills or RSCs. Farmer financing was entirely overlooked.
  - For HF in Ghana, A2F was better aligned with business needs, but needed significant handholding by HF to succeed.
  - The RSPO component was not relevant for SWAPP. This only makes sense if the product is exported – at the time of the evaluation the local market could absorb it all.
  - The nutrition component was an add-on, more like an afterthought. In CORIP and SWAPP, food production and intercropping received some attention, and HF promoted nutrition awareness. Although certainly useful for some families, a strategic and holistic approach to food and nutrition was absent in all three programmes. It was just not what these programmes were about; it was more about sector transformation and that may better have remained the core focus.

---
4. key findings - RELEVANCE (3)
Several core assumptions were not well tested. E.g.:
  - In CORIP and SWAPP, the core assumption was that through intensification, cocoa and oil palm would be an attractive earnings proposition, but in practice returns remain meagre, in part because of low prices
  - As a result, youth continue to flee the village and maybe become absentee farmers on their inherited farms => not realistic to expect them to stay (better to encourage them to pursue outside options?)
  - Women continue to face cultural obstacles to take up cocoa and oil palm farming (e.g. access to land)
  - The programme focused on including youth and women in RSCs but this would not create large numbers of jobs
Some core FNS assumptions of the FNS ToC (2019) did not hold:
  - One key assumption was that “food markets can be made inclusive for large numbers of smallholders” (“increasing scale, consolidation and reduction of farm numbers are no historic necessity”)
    - This did not hold for cocoa and oil palm

---
4. key findings - effectiveness (1)

---
4. key findings - effectiveness: Outputs vs outcomes
It was found that the programmes are generally effective in generating outputs, but far less so in producing outcomes and impacts. Such ineffective components are not sustainable either.
Examples:
  - The RSPO and RSC components in SWAPP
  - Youth employment in SWAPP
  - Youth and women inclusion in SWAPP and CORIP
  - HF work in Côte d'Ivoire
  - While it is recognised that in tree cropping outcomes may take some time to show themselves, in some cases programme design and (lack of) relevance are to blame.

---
4. key findings - effectiveness: ToC and MEL (1)
Both CORIP and SWAPP had excessively complex ToCs with over 100 results indicators:
  - Some indicators did not seem relevant (e.g., Hunger)
  - Some indicators could not be measured (CO2 reduction)
  - About 400 data points to collect for over 100 indicators
  - Disaggregation by country (4 countries), gender, youth, etc.
HF’s M&E framework was stronger, but indicators were not reported by country or sector, making it difficult to assess country-specific or sector-specific results
  - Unclear at first sight that results for 1 country were much better than in another country
  - Impossible to compare sectoral results with sector benchmarks (should have been required)
All programmes had limited baseline information and lacked control groups or other counterfactuals, making it difficult to attribute any observed results to programme activities.
  - Better baseline estimates should have been collected
  - Cost benefit analysis for collecting control group data should have been conducted at the very outset
  - In absence of control group data, sector benchmarks should have been developed/collected
  - Same finding in recent April 2022 discussion on MEL at RVO following FDOV evaluation

---
4. key findings - effectiveness: ToC and MEL (2)
There were several reasons for the complexity of the ToCs and M&E frameworks:
    - Many programmatic demands were made by EKN/MFA, not all of which appeared justifiable.
      - Some FNS indicators in CORIP and SWAPP, CO2 reduction
      - Request to incorporate gender and youth inclusion and ecological targets was not a direct fit in the case of HortiFresh
      - RBM indicators, added after the start of the programmes
    - SWA had limited human resources for its many M&E activities, resulting in missing data and calculation errors in spreadsheets (for CORIP in particular).
    - EKN Accra and relevant Dutch MFA departments (IGG, IOB) also had limited M&E capacity available for assessing the ToC and the M&E reports of the programmes
  - The overly complex M&E frameworks hampered not only the effectiveness of the programmes, but also their relevance, efficiency, impact and sustainability.
    - Lack of focus due to "must haves"
    - Time and money spent on data collection

---
4. key findings – Efficiency

---
4. key findings - sustainability

---
5. BROADER FINDINGS AT MFA LEVEL
Many FNS programmes suffer from weak or overly complex ToCs and M&E frameworks. This includes a lack of baselines, control groups and counterfactuals. The BEMO barely addresses this, and does not seek sufficient reassurances.
Embassies often do not have sufficient capacity to validate M&E data received from programmes, hence they report data in RBM that could be wrong.
IGG’s role in supporting embassies is limited. Once an (IGG-financed) programme is approved, embassies handle all implementation. Reports are not usually shared with IGG.
IOB also has capacity constraints and is not systematically involved in programme design, selection of implementing partners, ToC design or review, or review of M&E reports.
Overall, monitoring of ongoing FNS programmes by embassy staff or IGG/IOB is limited. Field visits are infrequent.
Ministry and embassies face funding constraints to increase staff capacity, but there may be less constraints for hiring engage external advisors.

---
5. BROADER FINDINGS AT MFA LEVEL
Classifying a PSD-oriented programme as FNS is quite common
  - Some FNS programmes (e.g., CORIP, SWAPP, 2SCALE) may better fit the DDE “Aid and Trade” agenda)
  - If classified as PSD, these programmes potentially be more effective by de-emphasising FNS objectives and concentrating more on sustainable private sector development (simpler ToC, more focus)
Several other IOB evaluations* came to similar conclusions regarding M&E frameworks:
  - Focus on meeting outputs targets instead of outcomes and impacts
  - Implicit and unproven assumptions in ToC
  - Lack of critical reflection on relevance and effectiveness
  - Fragmentation of interventions
  - Pressure to report on standard result indicators, which may become a ‘paper exercise’, with too little attention to learning in M&E and adaptation of the programme if so required
    - VSLA component is the positive exception
  1. * E.g., evaluation of "Wederopbouw programma (2012-2015), Strategische Partnerschappen Chronische Crises programma, (2014 - 2016) en het Addressing Root Causes tender proces" (2019)

---
6. CONCLUSIONS AND RECOMMENDATIONS - RELEVANCE

---
6. CONCLUSIONS AND RECOMMENDATIONS – EFFECTIVENESS (1)

---
6. CONCLUSIONS AND RECOMMENDATIONS – EFFECTIVENESS (2)

---
6. CONCLUSIONS AND RECOMMENDATIONS - EFFICIENCY

---
6. CONCLUSIONS AND RECOMMENDATIONS – SUSTAINABILITY (1)

---
6. CONCLUSIONS AND RECOMMENDATIONS – SUSTAINABILITY (2)